## WBS & Gantt
📋 LLM Wiki WBS & Gantt Chart
WBS | Task | Owner | Status | Start Date | Finish Date | W. | % | 10주 | 11주 |  | 12주 | 13주 | 14주 | 15주
Gantt
1 | 기획 및 설계 |  | -
1.1 | 프로젝트 기획 |  | Completed | 2026-05-12 | 2026-05-14 | 3 | 100
1.1.1 | 비전 및 요구사항 정의 |  | Completed | 2026-05-12 | 2026-05-13 | 2 | 100
1.1.2 | 주요 기능 및 보안 요구사항 정리 |  | Completed | 2026-05-13 | 2026-05-14 | 2 | 100
1.2 | 아키텍처 의사결정 정리 |  | Completed | 2026-05-14 | 2026-05-18 | 5 | 100
1.2.1 | 로컬 우선 구조 ADR 작성 |  | Completed | 2026-05-14 | 2026-05-15 | 2 | 100
1.2.2 | BYOK / 마크다운 / 플러터 ADR 작성 |  | Completed | 2026-05-15 | 2026-05-18 | 4 | 100
1.3 | 발표 및 프로젝트 문서화 |  | Completed | 2026-05-18 | 2026-05-20 | 3 | 100
1.3.1 | PRD / ADR / README 정리 |  | Completed | 2026-05-18 | 2026-05-20 | 3 | 100
1.4 | 1차 산출물 점검 |  | Milestone | 2026-05-20 | 2026-05-20 | 1 | 100 |  |  | ◆
2 | 개발 환경 구축 |  | -
2.1 | 프로젝트 초기화 |  | Completed | 2026-05-19 | 2026-05-21 | 3 | 100
2.1.1 | Flutter 프로젝트 생성 |  | Completed | 2026-05-19 | 2026-05-20 | 2 | 100
2.1.2 | GitHub Repository 및 Pages 설정 |  | Completed | 2026-05-20 | 2026-05-21 | 2 | 100
2.2 | 기본 앱 UI 구성 |  | Completed | 2026-05-21 | 2026-05-25 | 5 | 100
2.2.1 | 라이브러리 / 캡처 / 내보내기 / 보안 화면 |  | Completed | 2026-05-21 | 2026-05-23 | 3 | 100
2.2.2 | 발표용 GitHub Pages 구성 |  | Completed | 2026-05-23 | 2026-05-25 | 3 | 100
2.3 | 개발 환경 점검 |  | Milestone | 2026-05-25 | 2026-05-25 | 1 | 100 |  |  |  | ◆
3 | 도메인 및 데이터 레이어 |  | -
3.1 | 도메인 모델 정리 |  | In progress | 2026-05-26 | 2026-06-01 | 7 | 35
3.1.1 | Conversation / Message / Project 모델 |  | In progress | 2026-05-26 | 2026-05-28 | 3 | 50
3.1.2 | Repository 인터페이스 분리 |  | Not Started | 2026-05-28 | 2026-06-01 | 5 | 0
3.2 | 로컬 데이터 저장소 구현 |  | Not Started | 2026-06-02 | 2026-06-08 | 7 | 0
3.2.1 | SQLite 스키마 및 초기화 |  | Not Started | 2026-06-02 | 2026-06-05 | 4 | 0
3.2.2 | 대화/메시지/태그 Repository 구현 |  | Not Started | 2026-06-05 | 2026-06-08 | 4 | 0
3.3 | 중간 점검: 데이터 저장 구조 확인 |  | Milestone | 2026-06-01 | 2026-06-01 | 1 | 0 |  |  |  |  | ◆
4 | AI 채팅 및 지식화 기능 |  | -
4.1 | OpenAI API 연동 |  | Not Started | 2026-06-02 | 2026-06-08 | 7 | 0
4.1.1 | BYOK 기반 API 키 입력/검증 |  | Not Started | 2026-06-02 | 2026-06-04 | 3 | 0
4.1.2 | 채팅 요청/응답 Provider 구현 |  | Not Started | 2026-06-04 | 2026-06-08 | 5 | 0
4.2 | 지식화 자동 처리 |  | Not Started | 2026-06-09 | 2026-06-13 | 5 | 0
4.2.1 | 태그 생성 및 코드 스니펫 추출 |  | Not Started | 2026-06-09 | 2026-06-11 | 3 | 0
4.2.2 | 요약 생성 및 프로젝트 분류 보완 |  | Not Started | 2026-06-11 | 2026-06-13 | 3 | 0
5 | 검색, 내보내기, 보안 |  | -
5.1 | 검색 기능 구현 |  | Not Started | 2026-06-09 | 2026-06-13 | 5 | 0
5.1.1 | 제목/본문/태그 검색 |  | Not Started | 2026-06-09 | 2026-06-11 | 3 | 0
5.1.2 | 검색 필터 및 결과 정렬 |  | Not Started | 2026-06-11 | 2026-06-13 | 3 | 0
5.2 | 마크다운 내보내기 |  | Not Started | 2026-06-12 | 2026-06-16 | 5 | 0
5.2.1 | Export 포맷 및 Frontmatter 정리 |  | Not Started | 2026-06-12 | 2026-06-14 | 3 | 0
5.2.2 | 파일 저장 / 공유 기능 연결 |  | Not Started | 2026-06-14 | 2026-06-16 | 3 | 0
5.3 | 보안 기능 구현 |  | Not Started | 2026-06-14 | 2026-06-18 | 5 | 0
5.3.1 | Secure Storage / 민감정보 마스킹 |  | Not Started | 2026-06-14 | 2026-06-16 | 3 | 0
5.3.2 | 앱 잠금 / DB 암호화 검토 |  | Not Started | 2026-06-16 | 2026-06-18 | 3 | 0
6 | 테스트 및 발표 준비 |  | -
6.1 | 기능 테스트 |  | Not Started | 2026-06-17 | 2026-06-20 | 4 | 0
6.1.1 | 위젯 테스트 / 정적 분석 |  | Not Started | 2026-06-17 | 2026-06-18 | 2 | 0
6.1.2 | 모바일/웹 화면 점검 |  | Not Started | 2026-06-18 | 2026-06-19 | 2 | 0
6.2 | 최종 발표 준비 |  | Not Started | 2026-06-19 | 2026-06-20 | 2 | 0
6.2.1 | GitHub Pages 발표자료 최종 수정 |  | Not Started | 2026-06-19 | 2026-06-20 | 2 | 0
6.3 | 최종 발표 및 제출 |  | Milestone | 2026-06-20 | 2026-06-20 | 1 | 0 | [7 empty] | ◆

## Summary
LLM Wiki WBS Summary
Metric | Value | Basis | Note
Total task rows | 44 | WBS detail rows | Group rows excluded
Completed | 14 | Status
In progress | 2 | Status
Not started | 24 | Status
Milestones | 4 | Status
Project window | 2026-05-12 ~ 2026-06-20 | 10주~15주 | Presentation schedule
Status | Count
Completed | 14
In progress | 2
Not Started | 24
Milestone | 4